## Lista de Tarefas
2022
Work Breakdown Structure
Task | Scrum Master | State | Start Date | End Date | % of Conclusion | Done/Delayed? | Week
Identify code smells | Margarida Carvalho | Done | 2022-10-11 | 2022-10-21 | 100% | Done | 1
Identify design patterns | Margarida Carvalho | Done | 2022-10-11 | 2022-10-21 | 100% | Done | 1
Review code smells | Margarida Carvalho | Done | 2022-10-11 | 2022-10-21 | 100% | Done | 1
Review design patterns | Margarida Carvalho | Done | 2022-10-11 | 2022-10-21 | 100% | Done | 1
Analyse project 2 | Filipe Santo | Done | 2022-10-21 | 2022-10-31 | 100% | Done | 2
Weekly meeting | Filipe Santo | Done | 2022-10-21 | 2022-10-31 | 100% | Done | 2
Solve doubts | Filipe Santo | Done | 2022-10-21 | 2022-10-31 | 100% | Done | 2
Formulas:
End Date = [Start Date]:[Start Date]+10