## Sheet1
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Task | Initial Estimate | 1 | 2 | 3 | 4 | 5 | 6 | 7
Create fork for GanttProject | 1 | 1
Clone branch repo | 5 | 1 | 2 | 1
Make GantProject run locally | 12 |  | 2 | 2 | 2 | 2 | 2 | 2
Find 3 code patterns | 15 |  |  |  |  | 3 | 4 | 8
Find 3 code smells | 15 |  |  |  |  | 3 | 4 | 8
Total | 48 | 2 | 4 | 3 | 2 | 8 | 10 | 18 | Progress Made
Ideal Burndown | 48 | 41.1429 | 34.2857 | 27.4286 | 20.5714 | 13.7143 | 6.8571 | 0
Actual Burndown | 48 | 46 | 42 | 39 | 37 | 29 | 19 | 1